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2013 Vanuatu Climate Zone Quiz

Background

Climate Zone 2012 was a joint initiative among the Vanuatu Ministry of Education, the USP PACE-SD Climate Adaptation Program, the SPC-GIZ Climate Adaptation Program, The EU Global Climate Change Alliance and Australian Aid.  Students from around the Pacific competed to demonstrate their knowledge on the science, impacts and adaptation solutions to climate change. 

Proposal: 

The Government of Vanuatu would like to organize a Climate Zone Quiz 2013, building on the success and generated interest of the previous year.  The annual Quiz will be facilitated by the Vanuatu Ministry of Education, USP Vanuatu, the Vanuatu Meteorology & Geohazards Department, and SPC-GIZ Climate Change, and financially supported by ______________________________. 


2012 Quiz in Brief: 
1. Vanuatu’s Ministry of Education pre-selected Vanuatu’s best schools to compete in the competition.  In 2012, these included: 
a) Matevulu
b) Ranwade
c) Onesua
d) Central school
e) Lycee lab

2. USP provided pre-prepared information on climate change to each selected school to study and prepare. (Note that some schools received the notes later than others).

3. Each school was invited to send a team to the competition which included 4 students and a teacher. The teams of schools have mixed ages and years such as Central school consist of all year 11 while Matevulu College consist of year 12 and 13; some complaints of unfairness arose. 
4. Invited school on outer islands (such as Matevulu and Ranwade) traveled to port Vila with airfares and accommodation sponsored by the organizers (at a cost of  vt4,000 per student each day of competition)

5. The competition was held at TBV station and video recorded for airing on TV. 

6. The competition was organized into 4 stages: 
a) Each school competes, with school points totaled up.  Schools with the highest number of points moved to the next round.  
b) Winning school from the final gets vt100, 000 for school and vt10,000 per student and also goes to Fiji to represent Vanuatu. The runner up receives 50,000 for the school and 4,500 per student. 
 
PROPOSAL FOR A 2013 VANUATU CLIMATE ZONE QUIZ
 
The competition of this year will be a national competition open to all secondary schools from The Torres Islands to Aneityum.  However for 2013, it is suggested that only students from year 11 will participate.  The reason for this is because the final competition will be held in November during which (years 10, 12 and 13) will be busy preparing for the mock and national exam while the year 11 have no exam on that month.

Step 1 Initial Selection- Nationwide! 
1. USP, VMGD, and GIZ will provide background information about climate change that is endorsed by NAB (including science, impacts, mitigation, adaptation, and special topics e.g. gender)  to all year 11 secondary schools (both English and French language schools)
2. Schools will be given three weeks to study the information.
3. 	 Each school will select 4 year11 students and a teacher to take part in the 2013 	competition
4. All teams will take a written ‘exam’ (in English and French translations). All schools will sit the same exam questions on the same date, which is to be treated as an official exam. There will be a coordinator or proctor present to ensure that schools are administering the exam fairly.  
5.  Completed exams are then sent back to the Ministry of Education for marking. 
 
Step2. Final Competition in port Vila
1. The school team from each province that has the highest mark will be selected to participate in the final competition in Vila (held the same week as the National CC Symposium). If in a province there is a tie between two or more schools, a playoff will be arranged either in person or by written exam.   Only one school per province will be invited to participate in the final competition! 
2. The competition will be videotaped and shown on Television blong Vanuatu. 
3. All travelling teams (4 students + 1 teacher) will be provided with accommodation and per diem while in Port Vila.  








List of Proposed Schools for Vanuatu Climate Zone 2013(by province)

TORBA
   ENGLISH SCHOOL   
· AREP SECOUNDRY SCHOOL
 SANMA
ENGLISH SCHOOL
· AORE ADVENTIST ACADEMY
· HOG HARBOUR JUNIOR SECOUNDRY SCHOOL 
· MATEVULU
· TATA JUNIOR SECOUNDRY SCHOOL                                                                  
FRENCH SCHOL
· COLLEGE DE LUGANVILLE/LYCEE
· COLLEGE DE MOLIVALIVU/ECOLE CENTRE/LYCEE
· COLLEGE DE SAINTE ANNE/ECOLE CENTRE
· COLLEGE TECHNIQUE DE SAINT MICHEL/CENTRE/LYCEE
PENAMA
FRENCH SCHOOL
· COLLEGE DE MELSISI/ECOLE CENTRE/LYCEE
ENGLISH SCHOOL
· RANWADI CHURCH OF CHRIST COLLEGE
· ST PATRICKS COLLEGE
· RENSARIE COLLEGE/CENTRE SCHOOL
MALAMPA
FENCH SCHOOL
· COLLEGE DE NORSUP/ECOLE CENTRE
· COLEGE D*ORAP/ECOLE CENTRE/LYCEE
· COLLEGE DE RENSARIE/ECOLE CENTRE
ENGLISH SCHOOL
· RENSARIE COLLEGE/CENTRE SCHOOL
SHEFA
FRENCH SCOOL
· COLLEGE DE MONTMARTRE/LYCEE
· ECOLE FRANCAISE
· LYCEEE LOUIS ANTOINE DE BOUGAINVILLE
ENGLISH SCHOOL
· CENTRAL SECOUNDRY SCHOOL
· EPAUTO SDA SECOUNDARY SCHOOL
· EPI HIGHT SCHOOL
· MALAPOA COLLEGE
· ONESUA PRESBYTERIAN COLLEGE
· PORT VILA INTERNATIONAL
· SOROVANGA SECOUNTRY SCHOOL
TAFEA
FRENCH SCHOOL
· COLLEGE DE LOWANATOM/ECOLE CENTRE
· COLLEGE D*ISANGEL/ECOLE CENTRE
· COLLEGE DE TAFEA/ECOLE CENTRE
ENGLISH SCHOOL
· LENAULA JUNIOR SECOUNDRY SCHOOL
· KWATAPAREN JUNIOR SECOUNDRY SCHOOL/CENTRE
· LENAKEL JUNIOR SECOUNDRY SCHOOL/CENTRE
· TAFEA COLLEGE
· ISANGEL COLLEGE

 















[bookmark: _GoBack]Calendar of Events Leading to Climate Zone 2013 


	DATE
	OBJECTIVE
	THINGS TO CONSITERS
	STEPS AND WHAT TO DO

	3 April , 2013 
	CAME  UP WITH A MOTHLY PLAN
	
	

	APRIL
· 10/ 04/2013
· 29-30/04/2013
 
	
2en meeting

Funding



	
Renew draft budget
Names of funding group 
	

	MAY
· 2-8/05/2013



· 22/05/2013



	
Sending of invitation to schools 
All information are collected and conformation from school 


	
Contract/ email of principal and school
DVDs and hard copies
	

	JUNE

· 14-21/06/2013


· 10-14/06/2013



	
Meeting with partners to select their questions

Send study information to schools.
	
	USP, VMGD, and GIZ will provide note information about climate change to all year 11 secondary schools (both English and French language schools)  (week 1-2)

Each school will select 4 year11  students and a teacher to take part competition

Schools will be given three weeks to study the information. (stars at 17/06/203)


	JULY


· 16-20/08/2013









· 26-30/08/2013



	


Siting of the test  and sending back of the tests.
 






Mark of exams
	
	Schools will be given three weeks to study the information.
  
 GIZ and Ministry of Education will formulate written ‘exam’ questions (in English and French translations) for the 4 students to answer and return to GIZ. All school will sit the same exam questions, which are to be treated as an official exam. There will be a coordinator or proctor present to ensure that schools are administering the exam fairly.


.  Completed exams are then sent back to Ministry of Education and GIZ to mark.
  

	AUGUST
· 5-16/08/2013
	
Sent back the feed back to schools and the select school  sent the other 5 recourses

	
	
The school team from each province that has the highest mark will be selected to participate in the final competition in Vila. If in a province there is a tie between two or more schools, a playoff will be arranged either in person or by written exam.   Only one school per province will be invited to participate in the final competition!

	SEPTEMBER & OCTOBER




	School team revision and study 
	
	

	NOVEMBER
· 4-8/11/2013

	
Competition held simultaneously with National Climate Change Symposium
	

	
The competition will be videotaped and shown on Television blong Vanuatu.


	DATE
	DESCRIPTION
	NUMBER OF PARTIPITION
	AMOUNT

	
	RESOURCES INFORMAITION (DVD) 
	TORBA SCHOOL(1)
	VT 2500


	
	
	SANMA SCHOOL(8)
	VT 20000

	
	
	PENAMA SCHOOL(4)
	VT 10000

	
	
	MALAMPA SCHOOL(4)
	VT 10000

	
	
	SHEFA SCHOOL(10)
	VT 25000

	
	
	TAFEA SCHOOL(8)
	VT 20000

	
	
	TOTAL COST
	VT 87,500

	
	
VBTC
	
Equipment and venue
	
VT 1,149,885

	
	AIR FAIRS
	TORBA (5 ADULS)
	VT 390,000

	
	
	SANMA (5 ADUL)
	VT 155,900

	
	
	PENAMA (5 ADULT)
	VT 132,300

	
	
	MALAMPA (5 ADULT)
	VT 124,400

	
	
	TAFEA (5 ADULT)
	VT 135,900

	
	
	TOTAL COST 
	VT 938,500

	
	ACCOMONTAITION (vila hibibus)
	
	

	
	
	SANMA (5 DAYS)
	VT 37,500 

	
	
	PENAMA (5 DAYS)
	VT 37,500

	
	
	MALAMPA(5 DAYS)
	VT 37,500

	
	
	TAFEA (5 DAYS)
	VT 37,500

	
	
	TOTAL COST
	VT 150,000

	
	
	
	

	
	ALLOWANCES
	
	

	
	
	SANMA (5 HEADS)
	VT 62,500

	
	
	PENAMA (5 HEADS)
	VT 62,500

	
	
	MALAMPA (5 HEADS)
	VT 62,500

	
	
	TAFEA ( 5 HEADS)
	VT 62,500

	
	
	TOTAL COST
	VT 250,000

	
	
	
	

	
	PRIZES
	FIRST PLANCE(STUDENT 
SCHOOL)
	VT 50,000
VT 100,000

	
	
	SECOUND PLANCE (STUDENT
SCHOOL)
	
VT 22,500
VT 50,000

	
	
	TOTAL COST
	VT 222,500

	
	
	
	

	
	
	OVERALL COST TOTAL
	VT 2,798,385
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