Cyclone PAM: Food Security and Agriculture Cluster

Daily Briefing

Date 1 April 2015

1:00pm

Food Security and Agriculture Cluster 
Lead Organisations: DARD, SPC/GIZ, FAO

Urgent Needs:

- Long term rebuilding and restructuring of the Ministry (MLFFB) - Fishing gear (fish aggregating devices, backyard aquaculture, boats, nets etc) - Livestock fresh protein transport - Food rations for boarding schools - Animal welfare support (animal feed, water, shelter)

Response (high priority actions)

- International procurement of non-perishable emergency food stocks complete for next push of food WFP: 200MT rice, German Government: 137MT rice, Red Cross: 108MT, Adra: 25MT rice. Further procurement is underway for the for the longer term food assistance response. - First Push Food Distribution fully complete: SHEFA: Shepherds islands, Efate Offshore (3,100 people), Epi (7,600 people), TAFEA: (Aneityum, Aniwa, Futuna, MALAMPA (Paama) - TORBA: (Mere Lava; 100 households) - Food distribution close to completion: EFATE: Efate rural, Port Vila urban and peri-urban (18,500 households) TAFEA: Erromango (only Cooks Bay to be completed) MALAMPA (Ambrym, 1,500 households) - Food Distribution underway: PENAMA: (Pentecost, Maewo; 4,800 households), TAFEA (Tanna) - Dispatch and Distribution of High Energy Biscuits (HEB) to approximately 38,000 people in 9 priority islands with water shortages in Shefa and Tafea province; including dispatch of 31MT of HEB in Tanna - Provision of food assistance to boarding schools in Shefa and Tafea - Preparation of seed packages for distribution with the second push of food - Assessment of fisheries damage and of fish preservation and fishing facilities complete - Evaluation of availability of surplus fresh produce from less impacted islands has been undertaken including Fiji taro, island taro, cassava, kumula, yams, as well as for fishing by-catch. Transport and logistics options for these are being investigated. - Assessments on plant diseases and animal welfare on Epi is completed, need of water, shelter and animal feed - Development of long term recovery plan (forestry, fishery, agriculture)

Gaps & Constraints (beneficiary needs)

- Reliable statistics on number of households at the Area Council and village level. Detailed population counts are currently underway for Tanna and Efate - Detailed information by island and Area Council regarding delivery points for distribution and the population supported by these delivery points. - Improvements to the systemized reporting of people receiving food assistance