Cyclone PAM: Food Security and Agriculture Cluster

Briefing

Date 9 April 2015

5:00pm

Food Security and Agriculture Cluster 
Lead Organisations: DARD, SPC/GIZ, FAO

Urgent Needs:

- Rebuilding and rehabilitation of the MLFFB’s extension services which have been disrupted by the cyclone - Fishing gear (boats, nets etc) - Food assistance for boarding schools - Animal welfare support (animal feed, water, shelter)

Response (high priority actions)

- International procurement of non-perishable emergency food stocks is complete for the next push of food. The distribution plan for the second push of food assistance has been developed, with dispatch of food to priority one areas scheduled to commence this week. - The second push of food is targeting distribution to 180,000 individuals in Shefa, Tafea, Malampa (Paama and Ambrym) and Torba (Mere Lava). The key messages for recipient beneficiaries were published 8 April and broadcast by radio, outlining what households should expect during the distribution process. Updates on progress will be broadcast daily. - First push food distribution fully complete: SHEFA: Shepherds islands (4,400 people), Efate Offshore (3,100 people), Efate rural (6,800 people), Epi (7,600 people) TAFEA: Aneityum, Aniwa, Futuna, and Erromango (4,400 people) MALAMPA: Paama (3,600 people), (Ambrym, 1,500 households) TORBA: (Mere Lava; 100 households) EFATE: Port Vila urban and peri-urban (18,500 households) - First push food distribution underway: PENAMA: (Pentecost, Maewo; 4,800 households), TAFEA (Tanna) - Dispatch and Distribution of High Energy Biscuits (HEB) to approximately 38,000 people in 9 priority islands with water shortages in Shefa and Tafea province; including dispatch of 31MT of HEB in Tanna - Seed packages for priority one areas have been dispatched to be distributed via Area Councils. Distribution is underway in Tanna through NGOs and Area Councils. - Care International and Nasi Tuan are working with Department of Agriculture and Rural Development officers on Tanna on training for distribution, as well as techniques for improving soils to assist with seed growth - 20MT of fishing by-catch will arrive in Port Vila from Vanuatu flagged fishing vessels on Monday. This will be sold at a highly subsidized rate in the markets in poorer areas of Port Vila to increase access to protein. - Cutting materials for 2,000 households (kumula, manioc and island cabbage) have been transported from Santo and distributed in Efate, Efate offshore islands and the Shepherd Islands. Kumula cuttings have also been dispatched to Tanna for distribution. - The provision of day-old chickens and sufficient feed to raise them to 6 weeks of age has been completed on Pele, with the 30 households received 10 chickens each. If this trial is successful, it will be extended to other communities to provide an additional source of protein to households while their food sources are being re-established. - Transport of surplus fresh produce from less impacted islands including Fiji taro, island taro, cassava, kumula, yams, and is being evaluated for fishing by-catch. Fresh produce arrived in Port Vila on 2 April for sale at local markets. - Assessment of fisheries damage and of fish preservation and fishing facilities complete - Assessments on plant diseases and animal welfare on Epi is completed, identifying the need for water, shelter and animal feed. - First draft of medium and long term recovery strategy (forestry, fishery, agriculture) has been prepared and shared for feedback

Gaps & Constraints (beneficiary needs)

- Reliable statistics on number of households at the Area Council and village level. Detailed population counts are currently underway for Tanna and Efate - Detailed information by island and Area Council regarding delivery points for distribution and the population supported by these delivery points.