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Further information required

NAB Chair….……..……………..

Dated	         /        /


National Advisory Board on Climate Change and Disaster Risk Reduction
BRIEFING NOTE

TO:	 

SUBJECT:	Pacific Islands Coastal Community Adaptation Project (C-CAP)

TIMEFRAME
April 2012 to January 2014

RECOMMENDATION 

· C-CAP seeks NAB general project endorsement
· C-CAP seeks concurrence to work with Bani William (DAI preference) or NAB referral for another country-level coordinator to assist DAI with logistics
· C-CAP seeks concurrence for1st year work in 
· Tassiriki 
· Pele 
· C-CAP seeks recommendation for 3 additional sites in Efate that have completed V&As and have strong local governance.
· C-CAP’s Preferred choices: 
· Lelepa, 
· Blacksands, 
· Wiana and/or 
· Marou

BACKGROUND
Project focus: Community development; community infrastructure rehabilitation; disaster risk reduction; land use planning. Total funding:US$14,460,224 Funding source: United States Agency for International Development Funding Administrator: DAI/University of the South Pacific

CURRENT ISSUES
· Will begin implementation on 7 January 2013, with series of half day community workshops 
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