|  | ## REPUBLIC OF VANUATU NATIONAL ADVISORY BOARD ON CLIMATE CHANGE AND DISASTER RISK REDUCTION C/- VANUATU METEOROLOGY AND GEO-HAZARDS DEPARTMENT |  |
| --- | --- | --- |
| Private Mail Bag 9054, Port Vila; Telephone: (678) 22331; Fax: (678) 22310 Email: commp@meteo.gov.vu; Web: www.nab.vu (Address Correspondence to Director) |  |  |

CC/DRR Project Brief Form

| Project Title: SPARCK – Sharing Perceptions of Adaptation, Resilience and Climate Knowledge |  |
| --- | --- |
| Implementing Organisation/s: UNESCO Apidae Development Innovations | Project Contact Details: Mr. Rory Walshe Natural Sciences Department UNESCO Pacific Field Office P.O. Box 615 Matautu-Uta Apia Samoa |
| Duration: 6 Months total 1 week fieldwork in Vanuatu | Status: Active – currently running (Launched 22nd March 2013) |
| Total Funding: $100,000 USD | Funding Source/s: UNESCO Science Council |
| Mode of financing: Direct | Location & site/s: Based: UNESCO Pacific office, Apia Sites: Samoa Fiji Vanuatu |
| Scope: Community, National, Provincial, Regional | Project Type: Research, Community Awareness, Vulnerability Assessment, Educational Capacity Building |
| Sectors & Themes: Climate Change Adaptation, Climate Change Education, Risk Awareness, Science and Innovation, Technology | Other Government & Partner Agencies: Support from associated stakeholders: UNDP, UNEP, SPREP, USP (GCCA) Media Asosiesen blong Vanuatu (MAV), Vanuatu Climate Adaptation Network (VCAN) |
| Lead Government Department: Three sector focus Media: Media Asosiesen blong Vanuatu (MAV) Education: Department of Education Environment: Department of Environment | NAB Approval sought: [Please tick] - Partnership/implementation✓ - Final endorsement✓ |
| Objective/s: [100 words max] To better understand the perceptions of climate change problems and solutions in specific sectors (rural communities in conservation areas, media officers, high school teachers). SPARCK aims to identify gaps in knowledge and understanding and recognize ways to generate knowledge products that can be used to stimulate local level adaptation actions and provide useful resources in capacity building. The project aims to foster better communication and decision making on climate change as part of a wider objective on increasing climate literacy. It was developed based on research indicating that levels of understanding of climate change in Pacific communities are low. |  |
| Description: [1-2 paragraphs per topic max] - Outline key project components - Awareness raising / background work; this will involve seeking support from key ministries, establishing contacts, hiring a local project assistant, arranging venues, logistics and contacting participants. - Conducting focus groups; this involves bringing together 30-40 participants from targeted sectors to gather perceptual data with the assistance of a local facilitator. - Mobile Survey; an innovative mobile survey, the first of its kind in Vanuatu and the Pacific, will be implemented to survey participants. The mobile questionnaire is informed by the results of the focus groups and relies on awareness raising (all of which will be singularly about the survey and not climate change) through local radio, word of mouth, and posters to allow geographically remote participants to take part. - Dissemination of findings and results; once the data is analyzed and collected it will be distributed to all stakeholders to inform capacity building activities. - How will it be implemented? Following intensive awareness raising and planning in conjunction with a local project assistant, the researchers (UNESCO + Apidae) will travel to Vanuatu to conduct focus groups in three sectors (education, media and conservation area communities), these will be two hour interactive discussions about climate change involving 30-40 people. The fieldwork will last one week including the promotion of the mobile phone based survey. - Will the project fund local positions? Where? The project will require hiring a local Project Assistant for approx. 10 working days to prepare and conduct background work in preparation for the focus groups and mobile survey. A Terms of Reference for applicants will be circulated though local contacts and UNESCO’s National Commission. - How does the project link to GoV priorities (PAA)? The project links to the key sector of Environment and Disaster Management within the Primary Sector Development and Environment chapter of the GoV PAA 2006-2015. Specifically this project will contribute to; ‘conduct community awareness of the need to protect the environment including through reduction of risks from natural hazards’, since our study will enable targeted and accurate awareness strategies to be designed based on knowledge gaps. It will also enable the development of risk reduction programs in communities, highlight the importance of conservation areas in the fight against climate change and increase climate change literacy in education. - What related projects are being undertaken in the area? There are a multitude of climate change projects being undertaken which aim to provide similar adaptation outcomes. These include CCCPIR from SPC-GIZ, USP’s GCCA project and SPREP’s PACC among many more including several initiatives from UNESCO such as climate change education from CCESD. This project aims to complement the already existing work in the area as well as fit in with regional frameworks such as the Pacific Islands Framework for Action on Climate Change 2006-2015 (PIFACC), the Regional Framework for Action on Disaster Risk Management (2005-2015) (RFADRM) and Pacific Framework for Education for Sustainable Development. - Potential overlaps/duplication to be resolved Due to our specific focus on the key sectors (teachers, media and conservation area communities), our perceptual data will contribute to, and complement, existing projects. Duplication of existing studies and projects into risk and impact awareness of climate change is not a concern, firstly due to the lack of existing studies with a climate perceptions focus, secondly due to our specific sector focus and finally due to the complementary nature of updating and improving the resolution of perceptual data on the rapidly evolving subject of climate change. - Risk Management Strategies A component of our project management has been the maintenance of a risk management matrix. The project is inherently low risk due to its targeted focus and the fact that funding has been secured already. Additionally, Vanuatu represents the third and final country for the project so we will have learned lessons from our work in Samoa and Fiji, and refined our strategy and process from previous work. |  |
| How does the project link to GoV priorities: (NAB agenda, NAPA, New CC/DRR Policy….) The project links to the key sector of Environment and Disaster Management within the Primary Sector Development and Environment chapter of the GoV PAA 2006-2015. Specifically this project will contribute to ‘conduct community awareness of the need to protect the environment including through reduction of risks from natural hazards’ since our study will enable targeted, locally appropriate and relevant climate change awareness strategies to be designed based on knowledge gaps. It will also enable the development of risk reduction programs in communities; highlight the importance of conservation area management in responding to climate change, and increase climate change literacy in education. |  |
| Progress to date and current activities: [100 words max] Since the project’s launch in March, we have completed both our Samoan and Fijian data collection phases through in country focus groups and mobile surveys. These first two countries have been a successful trial of the use of our groundbreaking mobile survey. We are currently finalising our report document to disseminate our results for Samoa and beginning to develop our findings report for Fiji. We intend to carry out the same methodology in Vanuatu that we did in Samoa and Fiji. |  |
| Outputs: [IEC Materials, guidelines & handbooks, certified trainings, resources….] The primary output of the first phase of the project will be an improved understanding of how Pacific people perceive and relate to the concept of climate change, and how this can be use to improve climate change education and awareness. These findings will be published via an e-document and disseminated through the UNCTs of the Pacific and UNESCO Apia website in addition to public announcements and distribution to regional and local stakeholders. The intention of this output is to inform and enable capacity building activities to effectively address vulnerability and increase climate change literacy. In the second phase of the project, capacity building activities will be carried out in one country (Samoa, Fiji or Vanuatu) based on the findings of the survey work in Phase 1. These activities may take the form of teaching or media training materials or community workshops. |  |